## Product Backlog
Product Backlog
Task # | Sprint # | Task description | Status | Maintainer | Date added | Date completed | Hours to complete | Work points assigned | Sprint view key
1 | 1 | Basic webpage and repo setup | Done | chropic | 2026-09-09 | 2026-09-11 | 0.5 | 25 | 1-1
2 | 1 | Actual web interface and demo features | Done | chropic | 2026-09-09 | 2026-09-16 | 2 | 55 | 1-2
3 | 1 | Find client and update README | Done | chropic | 2026-09-09 | 2026-09-18 | 1 | 15 | 1-3
4 | 2 | German language toggle | Completed | chropic | 2026-09-23 | 2026-09-28 | 2.5 | 45 | 2-1
5 | 2 | Updated Search Feature (Frontend) | Completed | oogwaysprophecy732 | 2026-09-23 | 2026-09-23 | 2 | 45 | 2-2
6 | 2 | Server-side RSS Feed | Working | oogwaysprophecy732/chropic | 2026-09-23 |  |  |  | 2-3
7 | 2
|  | Define bias detection-what does bias look like (research included) | Backlog |  |  |  |  | 50
|  | Prototype bias detection model | Backlog |  |  |  |  | 150
|  | Stable increment of bias detection model | Backlog |  |  |  |  | 200
|  | Better UX with distinct language (close to/final sprint) | Backlog |  |  |  |  | 50
|  | Fine tune Docker container performance options, resource limits, security hardenings. | Backlog |  |  |  |  | 10
|  | Server-side optimizations and hardenings | Backlog |  |  |  |  | 35
|  | Website name and branding(?) | Backlog |  |  |  |  | 15

## Burndown Chart
Project Burndown ¦ Sprints 1–6 | Project Burndown ¦ Sprints 1–6 | Project Burndown ¦ Sprints 1–6 | Project Burndown ¦ Sprints 1–6 | Project Burndown ¦ Sprints 1–6 | Project Burndown ¦ Sprints 1–6 | Project Burndown ¦ Sprints 1–6 | Project Burndown ¦ Sprints 1–6 | Project Burndown ¦ Sprints 1–6 | Project Burndown ¦ Sprints 1–6 | Project Burndown ¦ Sprints 1–6 | Project Burndown ¦ Sprints 1–6 | Project Burndown ¦ Sprints 1–6
Remaining work units are calculated from Product Backlog completion dates and work points. The chart stops at the latest qualifying completion date.
[10 empty] | Sprint | Start date | End date
[10 empty] | 1 | 2026-09-09 | 2026-09-18
[10 empty] | 2 | 2026-09-23 | 2026-10-02
[10 empty] | 3 | 2026-10-07 | 2026-10-16
[10 empty] | 4 | 2026-10-21 | 2026-10-30
[10 empty] | 5 | 2026-11-04 | 2026-11-13
[10 empty] | 6 | 2026-11-18 | 2026-12-02
[10 empty] | Starting work units | 1000
[10 empty] | All work points assigned | 695
[10 empty] | Completed points recorded | 185
[10 empty] | Remaining work units now | 815
[10 empty] | Chart through | 2026-09-28
Date | Sprint or completion label | Remaining work units | Completed work points | [9 empty] | Sprint / completed date | Remaining work units | Ideal remaining work units
2026-09-09 | Sprint 1 (9/9) | 1000 | 0 | 1000 | [8 empty] | Sprint 1 (9/9) | 1000 | 1000
2026-09-10 |  | 1000 | 0 | 988.0952 | [9 empty] | 1000 | 988.0952
2026-09-11 | 9/11 | 975 | 25 | 976.1905 | [8 empty] | 9/11 | 975 | 976.1905
2026-09-12 |  | 975 | 0 | 964.2857 | [9 empty] | 975 | 964.2857
2026-09-13 |  | 975 | 0 | 952.381 | [9 empty] | 975 | 952.381
2026-09-14 |  | 975 | 0 | 940.4762 | [9 empty] | 975 | 940.4762
2026-09-15 |  | 975 | 0 | 928.5714 | [9 empty] | 975 | 928.5714
2026-09-16 | 9/16 | 920 | 55 | 916.6667 | [8 empty] | 9/16 | 920 | 916.6667
2026-09-17 |  | 920 | 0 | 904.7619 | [9 empty] | 920 | 904.7619
2026-09-18 | 9/18 | 905 | 15 | 892.8571 | [8 empty] | 9/18 | 905 | 892.8571
2026-09-19 |  | 905 | 0 | 880.9524 | [9 empty] | 905 | 880.9524
2026-09-20 |  | 905 | 0 | 869.0476 | [9 empty] | 905 | 869.0476
2026-09-21 |  | 905 | 0 | 857.1429 | [9 empty] | 905 | 857.1429
2026-09-22 |  | 905 | 0 | 845.2381 | [9 empty] | 905 | 845.2381
2026-09-23 | Sprint 2 (9/23) | 860 | 45 | 833.3333 | [8 empty] | Sprint 2 (9/23) | 860 | 833.3333
2026-09-24 |  | 860 | 0 | 821.4286 | [9 empty] | 860 | 821.4286
2026-09-25 |  | 860 | 0 | 809.5238 | [9 empty] | 860 | 809.5238
2026-09-26 |  | 860 | 0 | 797.619 | [9 empty] | 860 | 797.619
2026-09-27 |  | 860 | 0 | 785.7143 | [9 empty] | 860 | 785.7143
2026-09-28 | 9/28 | 815 | 45 | 773.8095 | [8 empty] | 9/28 | 815 | 773.8095
2026-09-29 |  | 815 | 0 | 761.9048 | [9 empty] | 815 | 761.9048
2026-09-30 |  | 815 | 0 | 750 | [9 empty] | 815 | 750
2026-10-01 |  | 815 | 0 | 738.0952 | [9 empty] | 815 | 738.0952
2026-10-02 |  | 815 | 0 | 726.1905 | [9 empty] | 815 | 726.1905
2026-10-03 |  | 815 | 0 | 714.2857 | [9 empty] | 815 | 714.2857
2026-10-04 |  | 815 | 0 | 702.381 | [9 empty] | 815 | 702.381
2026-10-05 |  | 815 | 0 | 690.4762 | [9 empty] | 815 | 690.4762
2026-10-06 |  | 815 | 0 | 678.5714 | [9 empty] | 815 | 678.5714
2026-10-07 | Sprint 3 (10/7) | 815 | 0 | 666.6667 | [8 empty] | Sprint 3 (10/7) | 815 | 666.6667
2026-10-08 |  | 815 | 0 | 654.7619 | [9 empty] | 815 | 654.7619
2026-10-09 |  | 815 | 0 | 642.8571 | [9 empty] | 815 | 642.8571
2026-10-10 |  | 815 | 0 | 630.9524 | [9 empty] | 815 | 630.9524
2026-10-11 |  | 815 | 0 | 619.0476 | [9 empty] | 815 | 619.0476
2026-10-12 |  | 815 | 0 | 607.1429 | [9 empty] | 815 | 607.1429
2026-10-13 |  | 815 | 0 | 595.2381 | [9 empty] | 815 | 595.2381
2026-10-14 |  | 815 | 0 | 583.3333 | [9 empty] | 815 | 583.3333
2026-10-15 |  | 815 | 0 | 571.4286 | [9 empty] | 815 | 571.4286
2026-10-16 |  | 815 | 0 | 559.5238 | [9 empty] | 815 | 559.5238
2026-10-17 |  | 815 | 0 | 547.619 | [9 empty] | 815 | 547.619
2026-10-18 |  | 815 | 0 | 535.7143 | [9 empty] | 815 | 535.7143
2026-10-19 |  | 815 | 0 | 523.8095 | [9 empty] | 815 | 523.8095
2026-10-20 |  | 815 | 0 | 511.9048 | [9 empty] | 815 | 511.9048
2026-10-21 | Sprint 4 (10/21) | 815 | 0 | 500 | [8 empty] | Sprint 4 (10/21) | 815 | 500
2026-10-22 |  | 815 | 0 | 488.0952 | [9 empty] | 815 | 488.0952
2026-10-23 |  | 815 | 0 | 476.1905 | [9 empty] | 815 | 476.1905
2026-10-24 |  | 815 | 0 | 464.2857 | [9 empty] | 815 | 464.2857
2026-10-25 |  | 815 | 0 | 452.381 | [9 empty] | 815 | 452.381
2026-10-26 |  | 815 | 0 | 440.4762 | [9 empty] | 815 | 440.4762
2026-10-27 |  | 815 | 0 | 428.5714 | [9 empty] | 815 | 428.5714
2026-10-28 |  | 815 | 0 | 416.6667 | [9 empty] | 815 | 416.6667
2026-10-29 |  | 815 | 0 | 404.7619 | [9 empty] | 815 | 404.7619
2026-10-30 |  | 815 | 0 | 392.8571 | [9 empty] | 815 | 392.8571
2026-10-31 |  | 815 | 0 | 380.9524 | [9 empty] | 815 | 380.9524
2026-11-01 |  | 815 | 0 | 369.0476 | [9 empty] | 815 | 369.0476
2026-11-02 |  | 815 | 0 | 357.1429 | [9 empty] | 815 | 357.1429
2026-11-03 |  | 815 | 0 | 345.2381 | [9 empty] | 815 | 345.2381
2026-11-04 | Sprint 5 (11/4) | 815 | 0 | 333.3333 | [8 empty] | Sprint 5 (11/4) | 815 | 333.3333
2026-11-05 |  | 815 | 0 | 321.4286 | [9 empty] | 815 | 321.4286
2026-11-06 |  | 815 | 0 | 309.5238 | [9 empty] | 815 | 309.5238
2026-11-07 |  | 815 | 0 | 297.619 | [9 empty] | 815 | 297.619
2026-11-08 |  | 815 | 0 | 285.7143 | [9 empty] | 815 | 285.7143
2026-11-09 |  | 815 | 0 | 273.8095 | [9 empty] | 815 | 273.8095
2026-11-10 |  | 815 | 0 | 261.9048 | [9 empty] | 815 | 261.9048
2026-11-11 |  | 815 | 0 | 250 | [9 empty] | 815 | 250
2026-11-12 |  | 815 | 0 | 238.0952 | [9 empty] | 815 | 238.0952
2026-11-13 |  | 815 | 0 | 226.1905 | [9 empty] | 815 | 226.1905
2026-11-14 |  | 815 | 0 | 214.2857 | [9 empty] | 815 | 214.2857
2026-11-15 |  | 815 | 0 | 202.381 | [9 empty] | 815 | 202.381
2026-11-16 |  | 815 | 0 | 190.4762 | [9 empty] | 815 | 190.4762
2026-11-17 |  | 815 | 0 | 178.5714 | [9 empty] | 815 | 178.5714
2026-11-18 | Sprint 6 (11/18) | 815 | 0 | 166.6667 | [8 empty] | Sprint 6 (11/18) | 815 | 166.6667
2026-11-19 |  | 815 | 0 | 154.7619 | [9 empty] | 815 | 154.7619
2026-11-20 |  | 815 | 0 | 142.8571 | [9 empty] | 815 | 142.8571
2026-11-21 |  | 815 | 0 | 130.9524 | [9 empty] | 815 | 130.9524
2026-11-22 |  | 815 | 0 | 119.0476 | [9 empty] | 815 | 119.0476
2026-11-23 |  | 815 | 0 | 107.1429 | [9 empty] | 815 | 107.1429
2026-11-24 |  | 815 | 0 | 95.2381 | [9 empty] | 815 | 95.2381
2026-11-25 |  | 815 | 0 | 83.3333 | [9 empty] | 815 | 83.3333
2026-11-26 |  | 815 | 0 | 71.4286 | [9 empty] | 815 | 71.4286
2026-11-27 |  | 815 | 0 | 59.5238 | [9 empty] | 815 | 59.5238
2026-11-28 |  | 815 | 0 | 47.619 | [9 empty] | 815 | 47.619
2026-11-29 |  | 815 | 0 | 35.7143 | [9 empty] | 815 | 35.7143
2026-11-30 |  | 815 | 0 | 23.8095 | [9 empty] | 815 | 23.8095
2026-12-01 |  | 815 | 0 | 11.9048 | [9 empty] | 815 | 11.9048
2026-12-02 | Sprint 6 end (12/2) | 815 | 0 | 0 | [8 empty] | Sprint 6 end (12/2) | 815 | 0

## Sprint 1
Sprint 1
Sprint 1 records and backlog view. Edit task details on the Product Backlog sheet; this view updates from the Sprint #.
Sprint # | 1 |  | Start date | 2026-09-09 |  | End date | 2026-09-18 |  |  | Historical note: Sprint 1 records Task #4’s RSS demo as implemented on 9/16/2026. The Product Backlog keeps the remaining RSS work assigned to Sprint 2, so Task #4 is not duplicated in this sprint’s automatic backlog view.
Sprint goal | Create a basic webserver and WebUI to serve over domain (esof423.csit.help) Wire up RSS implementation Find client
Tasks | 3 | Completed | 3 | Hours logged | 3.5 | Work points | 95
Auto-generated view. Do not enter tasks here; add or change them on Product Backlog.
Task # | Sprint # | Task description | Status | Maintainer | Date added | Date completed | Hours to complete | Work points assigned
1 | 1 | Basic webpage and repo setup | Done | chropic | 2026-09-09 | 2026-09-11 | 0.5 | 25 | 1
2 | 1 | Actual web interface and demo features | Done | chropic | 2026-09-09 | 2026-09-16 | 2 | 55 | 2
3 | 1 | Find client and update README | Done | chropic | 2026-09-09 | 2026-09-18 | 1 | 15 | 3

## Sprint 2
Sprint 2
Sprint 2 records and backlog view. Edit task details on the Product Backlog sheet; this view updates from the Sprint #.
Sprint # | 2 |  | Start date | 2026-09-23 |  | End date | 2026-10-02
Sprint goal | Build the German-language toggle and a country-aware filing-search prototype for U.S. and German companies.
Tasks | 3 | Completed | 2 | Hours logged | 4.5 | Work points | 90
Auto-generated view. Do not enter tasks here; add or change them on Product Backlog.
Task # | Sprint # | Task description | Status | Maintainer | Date added | Date completed | Hours to complete | Work points assigned
4 | 2 | German language toggle | Completed | chropic | 2026-09-12 | 2026-09-28 | 1 | 45 | 4
5 | 2 | Updated Search Feature (Frontend) | Completed | oogwaysprophecy732 | 2026-09-23 | 2026-09-23 | 2 | 45 | 5
6 | 2 | Server-side RSS Feed | Working | chropic | 2026-09-23 | 2026-09-25 | 3 | 15 | 6

## Sprint 3
Sprint 3
Sprint 3 records and backlog view. Edit task details on the Product Backlog sheet; this view updates from the Sprint #.
Sprint # | 3 |  | Start date | 2026-10-07 |  | End date | 2026-10-16
Sprint goal | Goal to be defined.
Tasks | 0 | Completed | 0 | Hours logged | 0 | Work points | 0
Auto-generated view. Do not enter tasks here; add or change them on Product Backlog.
Task # | Sprint # | Task description | Status | Maintainer | Date added | Date completed | Hours to complete | Work points assigned

## Sprint 4
Sprint 4
Sprint 4 records and backlog view. Edit task details on the Product Backlog sheet; this view updates from the Sprint #.
Sprint # | 4 |  | Start date | 2026-10-21 |  | End date | 2026-10-30
Sprint goal | Goal to be defined.
Tasks | 0 | Completed | 0 | Hours logged | 0 | Work points | 0
Auto-generated view. Do not enter tasks here; add or change them on Product Backlog.
Task # | Sprint # | Task description | Status | Maintainer | Date added | Date completed | Hours to complete | Work points assigned

## Sprint 5
Sprint 5
Sprint 5 records and backlog view. Edit task details on the Product Backlog sheet; this view updates from the Sprint #.
Sprint # | 5 |  | Start date | 2026-11-04 |  | End date | 2026-11-13
Sprint goal | Goal to be defined.
Tasks | 0 | Completed | 0 | Hours logged | 0 | Work points | 0
Auto-generated view. Do not enter tasks here; add or change them on Product Backlog.
Task # | Sprint # | Task description | Status | Maintainer | Date added | Date completed | Hours to complete | Work points assigned

## Sprint 6
Sprint 6
Sprint 6 records and backlog view. Edit task details on the Product Backlog sheet; this view updates from the Sprint #.
Sprint # | 6 |  | Start date | 2026-11-18 |  | End date | 2026-12-02
Sprint goal | Goal to be defined.
Tasks | 0 | Completed | 0 | Hours logged | 0 | Work points | 0
Auto-generated view. Do not enter tasks here; add or change them on Product Backlog.
Task # | Sprint # | Task description | Status | Maintainer | Date added | Date completed | Hours to complete | Work points assigned